Arm Health AI: 6-Month Work Plan (Nov 2025 - April 2026)

Project Goal: Develop and demonstrate a functional prototype/simulation of the AI-Driven Predictive Health Platform, including the LSTM model and the 3D Digital Twin visualization.

| Role/Major | Student Name | Focus Area |
| --- | --- | --- |
| Project Lead / Product Manager (Robotics, Master) | Marcos Dariel Cruces Delmar | Project Management, System Architecture, Visualization Interface |
| AI & Data Science Lead (AI, 2nd) | Zinuo Liu | Core AI (LSTM) Model Development, Remaining Useful Life (RUL) Prediction Algorithm |
| Robotics & Automation Engineer (IRE, 2nd) | Siyuan Qiu | Robot Simulation, Data Generation (Fault Injection), System Validation |
| Automation Engineer (ICTE, 4th) | Fernando Rosales Tello | Data Ingestion Pipeline (IoT Gateway Simulation), Real-time Data Handling |
| Automation Engineer (ICTE, 4th) | Rodrigo Axel Noeggerath Medina | Fault Optimization Logic, Maintenance Alert System, System Security/Reliability |
| Systems Integration Architect (IoT, 2nd) | José Manuel Cortés Cerón | Digital Twin Integration, 3D Visualization, Data Communication Protocols |

Phase 1: Data Acquisition & Core Model Development (Months 1-2)

The primary focus is securing a robust dataset (or simulating one) and building the core LSTM model for Remaining Useful Life (RUL) prediction.

| Month | Task / Deliverable | Allocation |
| --- | --- | --- |
| M1: Foundation & Data | T1.1: System Requirements & Architecture Finalization - - Define data points - Vibration, temperature, current, joint position - Sampling rates - The overall software stack - Cloud Computing Infrastructure - Software architecture - Back-end - Database - APIs - Front-end - Deliverable: System Architecture Document. | Marcos (Lead), José, Zinuo |
|  | T1.2: Data Simulation Environment Setup - - Set up a simulated industrial robot (e.g., in ROS/Gazebo or custom code) to generate synthetic operational and fault data (e.g., simulating motor bearing failure signatures) - Request changing data to Server - three.js Web scenario | Siyuan (Lead), Fernando |
|  | T1.3: Data Preprocessing Pipeline (IoT Ingestion Simulation) - - Develop Back-end - Database design MySQL - Develop APIs in Python - scripts to ingest, clean, normalize, and window the sensor data streams for the AI model. | Fernando (Lead), Rodrigo |
| M2: Core AI | T2.1: LSTM Model Architecture & Training Strategy - - Design the LSTM architecture - Define input/output tensors - Plan the supervised training approach for RUL prediction | Zinuo (Lead), Rodrigo |
|  | T2.2: Initial Model Training and Baseline RUL Calculation - - Train the first iteration of the LSTM model using simulated/sourced data - Establish a baseline accuracy for RUL prediction. | Zinuo (Lead), Marcos |
|  | T2.3: 3D Robot Model Sourcing/Creation - - Source or create a 3D model of a representative industrial robot arm for the Digital Twin visualization - Define how component health maps to the visual model. | José (Lead), Siyuan |

Phase 2: Integration & Digital Twin Development (Months 3-4)

The focus shifts to connecting the AI prediction to the visualization platform and building the real-time data flow.

| Month | Task / Deliverable | Allocation |
| --- | --- | --- |
| M3: Real-Time Integration | T3.1: AI Inference Pipeline Development - Implement the module to run the trained LSTM model in a low-latency environment, accepting real-time simulated data and outputting the RUL score. | Zinuo (Lead), Fernando |
|  | T3.2: Digital Twin Visualization Interface (V1) - Implement the front-end (web-based) interface to display the 3D robot model. Ensure it can receive and display the real-time RUL score for a single component/joint. | José (Lead), Marcos |
|  | T3.3: Data Reliability & Security Protocol Simulation - Implement mock mechanisms for data integrity checks and secure transmission from the "Edge Gateway" (simulated by the ingest script) to the "Cloud" (AI inference). | Rodrigo (Lead), Fernando |
| M4: Fault & Alert System | T4.1: Fault Detection & Optimization Logic - Develop the logic that defines the threshold (e.g., RUL < 72 hours) and automatically triggers a maintenance alert. Integrate this logic with the AI output. | Rodrigo (Lead), Zinuo |
|  | T4.2: Automated Alert System (V1) - - Create a functional simulation of the alert system (e.g., displaying a persistent notification or generating a simulated work order ticket) - N8N | Marcos (Lead), José |
|  | T4.3: Real-Time Kinematics Mapping - Ensure the Digital Twin accurately reflects the robot's real-time joint positions (using data from the simulated robot) while also displaying the predicted component health overlay. | Siyuan (Lead), José |

Phase 3: Validation, Refinement & Documentation (Months 5-6)

This phase is dedicated to extensive testing, improving prediction accuracy, and finalizing all project deliverables.

| Month | Task / Deliverable | Allocation |
| --- | --- | --- |
| M5: System Validation | T5.1: End-to-End System Stress Test - Run the complete system (Data Generator -> Ingestion -> AI Prediction -> Digital Twin -> Alert System) with simulated fault scenarios to test latency, accuracy, and alert reliability. | Siyuan (Lead), Fernando, Rodrigo |
|  | T5.2: AI Model Tuning & Optimization - Fine-tune the LSTM model to achieve the target >95% accuracy and ensure 72+ hours lead time on the simulated test data. Document model limitations. | Zinuo (Lead) |
|  | T5.3: User Experience (UX) Refinement of Digital Twin - Improve the aesthetic and usability of the 3D visualization and alert dashboard based on testing and best practices. | José (Lead), Marcos |
| M6: Finalization | T6.1: Final Project Report & Viability Analysis - Compile the full technical report, including methodology, results, and a detailed analysis of the business model (SaaS/HaaS) and market viability. | Marcos (Lead), Rodrigo |
|  | T6.2: Final Predictive Demonstration - Prepare and rehearse the final presentation, showcasing a simulated fault injection and the platform successfully predicting failure and triggering an alert. Deliverable: Final Presentation/Video. | All Students |
|  | T6.3: Comprehensive Documentation & Code Submission - Organize the codebase, API documentation for all modules (AI, IoT, 3D), and provide detailed setup instructions for future users. | Fernando (Lead), Siyuan, Zinuo, José |